## Sheet1
The Planning and Sizing Matrix provides guidance on the required artefacts for a project, depending on the type, size or complexity. This should be used as a guide only. Consultation with the Corporate Programme Office Centre of Excellence should be sought to confirm a projects expected artefacts.
| Planning & Sizing Matrix | NON ICT | BAU | SMALL | MEDIUM to LARGE | Explanatary comments
Phase | Artefacts
Concept Definition | Needs Assessment | No | No | No | Optional | For M/L projects, use if more detail required to specify need for the project, as-is and to-be states for business processes.
| Options Analysis | No | No | No | Optional | S projects only if project is Leading Edge architectural change. Optional for M and L Projects depending on proposed architecuture
| Investment Logic Map | Yes | No | Yes | Yes
| Expected Benefits | Yes | No | Yes | Yes
| Outline Business Case | Yes | No | Optional | Yes | For M/L projects, required to justify the need/viability of a project. S projects may include business case content in Project Brief.
| Project Brief | Yes | Yes | Yes | Yes | Always required to initiate and outline purpose of project.
| High Level Change Impact Assessment | Yes | No | Yes | Yes
Initiate / Plan | Draft High Level Business Requirements | Yes | Yes | Yes | Yes | Elicited from business users and documented to form a common understanding to enable planning.
| Project Initiation Document (PID) | Yes | No | No | Yes | Includes Project Plan, Revised Business Case, Comms Plan, Quality Plan (can separate these if required)
| Stage Plan(s) | Yes | No | No | Yes | Use if Project will be delivered in Stages
| High Level Schedule | Yes | No | No | Yes | Detailed schedule in PID or Brief adequate for S and BAU projects
| Risk Assessment | Yes | No | No | Yes | For S projects, summaryof risks included in Small Project Brief
| Proof of Concept (POC) Report | No | No | No | No | Use if Project Approach determines need.
| Communication Plan | Yes | No | Yes | Yes
| Draft Change Management Plan | Yes | No | No | Yes
| Small Project Plan | No | Yes | Yes | No | Used instead of PID for BAU projects to document any delivery plans or considerations.
| Revised Business Case | No | No | Yes | Yes | Included in PID or Small Project Plan. Confirms project aligns with organisational strategy and is a sound investment with benefits.
Execute / Delivery | Project Control Register | Yes | No | Optional | Yes | Register for Risks, Issues, Lessons Learned, Action Items. Available for S projects if needed.
| Project Schedule | Yes | Yes | Yes | Yes | Schedule of tasks, resources, dependencies, dates for all project work
| Project Budget Spreadsheet | Yes | No | No | Yes | To manage cost estimates and actuals
| Final Change Management Plan | Yes | No | No | Yes
| Training Plan | Yes | No | Yes | Yes | Required for any project with a training component.
| Solution Architecture/High Level Design | No | No | Yes | Yes | High level technical design planning, approved by ITAB.
| Final High Level Business Requirements | Yes | Yes | Yes | Yes | Approved by business users and documented to form an agreed set of requirements to enable delivery
| Project Test Plan | No | Yes | Yes | Yes | Always required if project has ICT component.
| Test Summary Report | No | No | No | Yes | Required if project has ICT component. May be used for S projects if required
| Deployment Plan | No | No | No | Yes | Required if project has ICT component. For S projects may be omitted or included in a PID.
| Systems Security Plan | No | No | No | Yes | Required if project has ICT component. May be used for S projects if required
| Transition Implementation Plan | No | No | No | Yes | Required if project has ICT component. May be used for S projects if required
| Transition Acceptance Checklist | No | No | Yes | Yes | Required if project has ICT component.
| Other ICT Delivery Framework Artefacts | No | No | Yes | Yes | Refer to ICT Delivery Framework for required artefacts
| Business Readiness Checklist | Yes | No | Yes | Yes
| End Stage Report | Yes | No | No | Yes | Use if Project will be delivered in Stages
| Procurement Plan (if required) | No | No | No | Yes | If appropriate, identify packages of work that will be vendor delivered, and how vendor selection will be conducted.
| Post Implementation Review Plan | Yes | No | Yes | Yes | Required for all higher complexity projects, but recommended for all projects with expected measureable benefits.
| Lessons Learned Report | Yes | No | No | Yes | For S projects may be included in Closure Report.
| End Project Report | Yes | No | No | Yes | For S projects a one page report highlighting work completed and any remaining issues is sufficient.
| Small Project Closure Report | No | Yes | Yes | No | For BAU and S project instead of End Project Report
| Final Acceptance Certificate | Yes | No | No | Yes | Optional for S projects, but may be used to confirm delivery to sponsor.
Benefits Review | Final Benefit Report | Yes | No | Optional | Yes | Required for all higher complexity projects, but recommended for all projects with expected measureable benefits.
Post Implementation Review Report
|  | NON ICT | BAU | SMALL | MEDIUM to LARGE
Governance
| Project Manager/Project Director | Yes | No | Yes | Yes | For BAU, the role of PM may be adopted by another individual (e.g. operational team lead).
| Project Board | Yes | No | No | Yes | For BAU and S projects, may be replaced by the operational team meeting chaired by the manager (equiv to the Project Exec)
| Small Project Progress Report | No | Yes | Optional | No | Sent to Project Exec equivalent on a weekly basis to report on progress (simplified highlight report).
| Highlight Report | Yes | No | Optional | Yes | Sent to Board and key stakeholders monthly (or as agreed in Project Board TORs). S projects may use Highlight or Small Progress Rpt
| IT Architecture Board (ITAB) | No | No | Yes | Yes | Architecture Board approval is always required for projects of Significant or Leading Edge architectural change.
| Programme Board | Yes | No | No | Yes | Programme Board direction/approval is needed for projects which are part of a programme of work
| Operations Committee | No | No | No | Yes | Operations Committee direction/approval is always needed for M & L projects.
| Gate 0 Review -- Approval to Proceed to Initiate/Plan | Yes | No | No | Yes | Required to approve Business Case and Project Brief, but gate review not required for BAU and S projects.
| Gate 1 Review -- Approval to Execute | Yes | No | No | Yes | Always required to release funding and resources.For BAU projects permission to execute is granted at gate 1.
| Gate 2 Review -- Deployment Readiness Review | Yes | No | No | Yes | For S projects detail planning can be combined with Feasibility, and permission to deliver granted at gate 1.
| Gate 3 Review -- Benefit Review & Closure | Yes | No | No | Yes | Closure report required, but gate review not required for S or M projects.
| Conduct Benefits Review | Yes | No | Optional | Yes | Benefits review optional for S or M projects.
Note: | Non ICT Projects may also be categorised as S, M, L, and follow the artefact list as required.
Refer to the Project Management Framework Project Sizing Guidelines to calculate size in conjunction with Corporate Programme Office and relevant business area.